## Others
# | Done? | Who? | Where? | What?
1 | 2022-02-08 | Mark | Level Selector | After completing the EASY level of forces, no stars is seen on the button
2 | 2022-02-08 | Mark | Level Selector | Limit the scrolling height of the level selector until force levels only
3 |  | Mark | Stunt Science Website | Update me if the initial pages are finished so we could setup it on a subdirectory of the witcrd.com website
4 | 2022-03-05 | Mark | About - Stunt Science | Add links of WIT, WVSU, and DOST to their respective websites. Make link fonts dark orange.
5 | 2022-02-08 | Nicko | App Logo | Implement a perspective style formula to the upper right corner of the logo.
6 | N/A | Mark | ALL STAGES | (CANCELLED - Anyway, we don't redisplay correct answer on success message) Any answer within the tolerance range should be the same value on all success messages
7 | 2022-02-23 | Mark | About - Research Team | Add Title of Ryan Subong - Director, Center of Research and Development, Western Institute of Technology
8 | 2022-02-18 | Mark | About - Soundtracks | Title of the Force Level Soundtrack: Zombie Force
9 | 2022-02-18 | Mark | About - Stunt Science | Add year to paragraph: "Stunt Science is a 2021 DOST-PCIEERD funded…"

## Velocity
# | Done? | Who? | Where? | What?
1 | 2022-02-16 | Michpaul | EASY, Stage 1 | Character should be in front of the "SAFE SPOT" arrow, not behind
2 |  | Michpaul | EASY, Stage 1 | Green fonts with white outline should be dark green color
3 | 2022-03-05 | Mark | EASY, Stage 1 | Grammar and spelling correction on SUCCESS message… [NAME] ran at the precise speed to stop exactly at the safe spot. Stunt successfully executed!
4 | 2022-02-23 | Mark | EASY, Stage 1 | On FAILED message… [NAME] too [fast/slow] and stopped way [after/before] the safe spot. Stunt failed! The correct answer is [ANSWER] m/s.
5 |  | Michpaul | EASY, Stage 1 | Prevent the player from interacting with the answer entry after closing the failed message and resetting the game.
6 | 2022-02-16 | Michpaul | EASY, Stage 2 | Character should be in front of the "SAFE SPOT" arrow, not behind
7 |  | Michpaul | EASY, Stage 2 | Green fonts with white outline should be dark green color
8 |  | Michpaul | EASY, Stage 2 | Animation error when the answered time is too long and the character runs way beyond the cliff. The character teleports to new position
9 |  | Michpaul | EASY, Stage 2 | Prevent the player from interacting with the answer entry after closing the failed message and resetting the game.
10 | 2022-02-18 | Michpaul | EASY, Stage 3 | Character should be in front of the "SAFE SPOT" arrow, not behind
11 |  | Michpaul | EASY, Stage 3 | Green fonts with white outline should be dark green color
12 | 2022-02-23 | Michpaul | EASY, Stage 3 | Remove torches outside wall area
13 |  | Michpaul | EASY, Stage 3 | (REVISED) Show distance lines of correct answer in GREEN and distance of wrong answer in RED if failed
14 |  | Michpaul | EASY, Stage 3 | Player should continue running, possibly hitting the wall if runs way past the manhole.
15 |  | Michpaul | MED, Stage 1 | Add rolling sound when boulder rolls, and a hit sound when player hits the boulder
16 |  | Michpaul | MED, Stage 1 | Add a "thud" sound when jumping
17 |  | Michpaul | MED, Stage 1 | The correct answer on the result message should be in green
18 | 2022-02-23 | Michpaul | MED, Stage 1 | (CRITICAL ERROR) Even after a successful stunt, the game ends! Game over!!!
19 |  | Michpaul | HARD, Stage 1 | Show distance lines of correct answer if failed
20 |  | Michpaul | HARD, Stage 1 | Add a "tsk" sound when throwing and also when hitting the monster incorrectly
21 |  | Michpaul | HARD, Stage 2 | Stop the timer at exactly 0.0s when time is up, not at negative value (ex. -0.01s)
22 |  | Michpaul | HARD, Stage 2 | Add a "tsk" sound when throwing and also when hitting the monster incorrectly
23 |  | Michpaul | HARD, Stage 2 | (sometimes) The slanting direction arrow of the moving monster is not parallel with the dragon path on the triangle diagram
24 |  | Michpaul | HARD, Stage 3 | Add a "tsk" sound when throwing and also when hitting the monster incorrectly
25 |  | Michpaul | HARD, Stage 3 | (sometimes) The slanting direction arrow of the moving monster is not parallel with the dragon path on the triangle diagram

## Acceleration
# | Done? | Who? | Where? | What?
1 |  | Jiboy | EASY, Stage 1 | After the elapse time, the acceleration should now be zero 0 and the velocity should have a steady value (not zero) because the motorcycle has stopped accelerating.
2 |  | Jiboy | EASY, Stage 1 | If the answer is correct, or less (the motorcycle stops acceleration before the jump), leave a shadow where the acceleration stops then indicate in that place the acceleration and the final velocity.
3 |  | Jiboy | EASY, Stage 1 | On Failed Message… [NAME] accelerated the motorcycle too [slow/fast] and was not able to cross the tunnel! The correct answer is [ANSWER] m/s2.
4 |  | Jiboy | EASY, Stage 1 | On Success Message… [NAME] drove the motorcycle at the precise acceleration to cross the tunnel! Stunt successfully executed!
5 |  | Jiboy | EASY, Stage 2 | Grammar… change the word "apply" to "applying". Add space after comma on the sentence.
6 |  | Jiboy | EASY, Stage 2 | Remove the distance indicator on the diagram because it is not mentioned in the worded problem.
7 |  | Jiboy | EASY, Stage 2 | If the answer is correct, or less (the motorcycle stops braking after a given time), leave a shadow the time runs out then indicate in that place the acceleration and the final velocity.
8 |  | Jiboy | EASY, Stage 2 | On Failed Message… [NAME] deaccelerated the motorcycle too [long/short] and it was running too [slow/fast] to cross the tunnel! Stunt failed! The correct answer is [ANSWER] s.
9 |  | Jiboy | EASY, Stage 2 | On Success Message… [NAME] deaccelerated the motorcycle at a precise duration to reduce its movement at the exact velocity to cross the tunnel! Stunt successfully executed!
10 |  | Jiboy | EASY, Stage 3 | On Failed Message… [NAME] initially drove the motorcycle too [slow/fast] and [did not stop/crashed] the motorcycle behind the truck. Stunt failed! The correct answer is [ANSWER] m/s.
11 |  | Jiboy | EASY, Stage 3 | On Success Message… [NAME] drove the motorcycle at the precise initial velocity to stop and park the motorcycle behind the truck! Stunt successfully executed!
12 | 2022-02-17 | Jiboy | MED, Stage 1 | Make the helicopter shadow more transperent
13 | 2022-02-23 | Mark | MED, Stage 1 | On Failed Message… [NAME] grabbed the rope too [soon/late] and missed it. Stunt failed! The correct answer is [ANSWER] seconds.
14 | 2022-02-23 | Mark | MED, Stage 1 | On Success Message… [NAME] grabbed the rope at the precise time and successfully hangs from it! Stunt successfully executed!
15 | 2022-02-17 | Jiboy | MED, Stage 1 | (CRITICAL ERROR) After a successful stunt, I could not proceed to the next stage. Pressing the play button do nothing.
16 | 2022-03-03 | Mark | MED, Stage 2 | On Failed Message… [NAME] kicked too [early before/late after] the van passed [him/her] and failed to hit the windsheild. Stunt failed! The correct answer is [ANSWER] meters.
17 |  | Mark | MED, Stage 2 | (GRAMMAR CORRECTION) On Success Message… [NAME] kicked at the exact distance to kick and hit the windsheild with a precise timing! Stunt successfully executed!
18 | 2022-03-03 | Jiboy | MED, Stage 2 | Add breaking glass sound when hitting the windsheild
19 | 2022-03-03 | Mark | MED, Stage 3 | On Failed Message… [NAME] accelerated the van too [fast/slow] and missed grabbing the rope precisely at the edge of the ledge. Stunt failed! The correct answer is [ANSWER] m/s2.
20 | 2022-03-03 | Mark | MED, Stage 3 | On Success Message… [NAME] drove the van with just the precise acceleration to grab the robe exactly at the edge of the ledge! Stunt successfully executed!
21 | 2022-03-03 | Jiboy | MED, Stage 3 | Add splash sound when the van hits the water
22 |  | Jiboy | HARD, Stage 1 | Time value at the worded problem is not displayed but a square character instead
23 |  | Jiboy | HARD, Stage 1 | On Failed Message… [NAME] shot the gun too [soon/late] and was unable to hit the wheel. Stunt failed! The correct answer is [ANSWER] s.
24 |  | Jiboy | HARD, Stage 1 | On Success Message… [NAME] shot the gun with a precise timing to hit the wheel! Stunt successfully executed!
25 |  | Jiboy | HARD, Stage 2 | Time value at the worded problem is not displayed but a square character instead
26 |  | Jiboy | HARD, Stage 2 | On Failed Message… The helicopter flew too [slow/fast] and [NAME] missed hitting the wheel. Stunt failed! The correct answer is [ANSWER] m/s.
27 |  | Jiboy | HARD, Stage 2 | On Success Message… The helicopter flew in just the precise velocity for [NAME] to hit the wheel! Stunt successfully executed!
28 |  | Jiboy | HARD, Stage 3 | Time value at the worded problem is not displayed but a square character instead
29 |  | Jiboy | HARD, Stage 3 | Does not accept the correct answer indicated at the DEBUG. Maybe rounding off error? Tolerance error?
30 |  | Jiboy | HARD, Stage 3 | On Failed Message… The helicopter accelerated too [slow/fast] and [NAME] missed hitting the wheel. Stunt failed! The correct answer is [ANSWER] m/s.
31 |  | Jiboy | HARD, Stage 3 | On Success Message… The helicopter flew in just the precise acceleration for [NAME] to hit the wheel! Stunt successfully executed!

## Projectile
# | Done? | Who? | Where? | What?
1 | 2022-02-09 | Jiboy | EASY, Stage 1 | If the correct abswer is 3.71m, the player is not allowed to enter more than 3.71 m? Cannot Answer 4m? 5m? Solution: Pull up the player before dropping if the entered answer is higher than the correct answer.
2 | 2022-02-09 | Jiboy | EASY, Stage 1 | Follow the time indicator with the falling player
3 | N/A | Jiboy | EASY, Stage 1 | (CANCELLED: No sound is ok) Add a "tsk" sound when letting go of the rope (same sound of grabbing the branch)
4 | 2022-02-09 | Jiboy | EASY, Stage 1 | If failed, leave a shadow figure of the player at the point where he did the grab and stop and rest the time indicator beside the shadow.
5 | 2022-02-09 | Mark | EASY, Stage 1 | On Failed Message… [NAME] let go of the rope too [high/low] and unable to grab the branch at the right time. Stunt failed! The correct answer is [ANSWER] meters.
6 | 2022-02-10 | Mark | EASY, Stage 1 | On Success Message… [NAME] let go of the rope at the precise distance from the branch ran and successfully grabs it! Stunt successfully executed!
7 |  | Jiboy | EASY, Stage 1 | Show distance between the rope and the branch after entry of answer and before animating the result
8 | 2021-02-17 | Jiboy | EASY, Stage 1 | [CRITICAL ERROR] Game does not continue on correct answer, it just hangs and do nothing after successfully grabbing the branch.
9 | 2022-02-18 | Jiboy | EASY, Stage 2 | Follow the time indicator with the falling player
10 | 2022-02-23 | Jiboy | EASY, Stage 2 | Add a "tsk" sound when letting go of the branch (same sound of grabbing the branch)
11 | 2022-02-18 | Jiboy | EASY, Stage 2 | If failed, leave a shadow figure of the player at the point where he did the grab and stop and rest the time indicator beside the shadow.
12 | 2022-02-15 | Mark | EASY, Stage 2 | On Failed Message… [NAME] grabbed the lower branch too [soon/late] and missed grabbing it. Stunt failed! The correct answer is [ANSWER] seconds.
13 | 2022-02-15 | Mark | EASY, Stage 2 | On Success Message… [NAME] grabbed the lower branch at the precise time and successfully hangs from it! Stunt successfully executed!
14 | 2022-02-17 | Jiboy | EASY, Stage 2 | (CRITICAL ERROR) After a successful stunt, I could not proceed to the next stage. Pressing the play button do nothing.
15 | 2022-02-23 | Jiboy | EASY, Stage 3 | Follow the time indicator with the falling player
16 | 2022-02-18 | Jiboy | EASY, Stage 3 | Add a "tsk" sound when letting go of the branch (same sound of grabbing the branch)
17 | 2022-02-23 | Jiboy | EASY, Stage 3 | Add a "thud" sound when the player failed and hits the ground.
18 | 2022-02-23 | Jiboy | EASY, Stage 3 | If failed, leave a shadow figure of the player at the point where he did the grab and stop and rest the time indicator beside the shadow.
19 | 2022-02-15 | Mark | EASY, Stage 3 | On Failed Message… [NAME] grabbed vine too [soon/late] and missed grabbing it. Stunt failed! The correct answer is [ANSWER] seconds.
20 | 2022-02-15 | Mark | EASY, Stage 3 | On Success Message… [NAME] grabbed the vine at the precise time and successfully hangs from it! Stunt successfully executed!
21 |  | Jiboy | MED, Stage 1 | (NOTE: EXACTLY AT THE CORNER) Point the arrow of the "Gripping Point" label precisely at the very corner of the cliff
22 | 2022-03-03 | Jiboy | MED, Stage 1 | Show the entered velocity on the arrow at start of animation
23 | 2022-02-23 | Mark | MED, Stage 1 | On Failed Message… [NAME] shot the gripping projectile too [slow/fast] and missed hitting the gripping point. Stunt failed! The correct answer is [ANSWER] m/s.
24 | 2022-03-05 | Mark | MED, Stage 1 | On Success Message… [NAME] shot the gripping projectile in just the precise velocity to hit the gripping point! Stunt successfully executed!
25 | 2022-02-23 | Jiboy | MED, Stage 2 | Label the target as the "Gripping Point"
26 | 2022-03-05 | Mark | MED, Stage 2 | On Failed Message… [NAME] aimed the gripping projectile too [high/low] and missed hitting the gripping point. Stunt failed! The correct answer is [ANSWER] m/s.
27 | 2022-03-05 | Mark | MED, Stage 2 | On Success Message… [NAME] aimed and shot the gripping projectile in just the precise angle to hit the gripping point! Stunt successfully executed!
28 | 2022-02-15 | Jiboy | MED, Stage 3 | Replace scenario.
29 | 2022-03-05 | Mark | MED, Stage 3 | On Failed Message… [NAME] aimed the gripping projectile too [high/low] and missed hitting the gripping point. Stunt failed! The correct answer is [ANSWER] m/s.
30 | 2022-03-05 | Mark | MED, Stage 3 | On Success Message… [NAME] aimed and shot the gripping projectile in just the precise angle to hit the gripping point! Stunt successfully executed!

## Circular Motion
# | Done? | Who? | Where? | What?
1 | 2022-02-23 | Michpaul | EASY, Stage 1 | Put "Landing Spot" on the target indicator
2 | 2022-02-23 | Michpaul | EASY, Stage 1 | Indicate the angular velocity of the gear as it spins
3 |  | Michpaul | EASY, Stage 1 | Make it a practice that the standard color for the correct answer is GREEN and the wrong answer is RED. Apply to both the diagram and the worded problem.
4 |  | Michpaul | EASY, Stage 1 | Green fonts with white outline should be dark green color
5 |  | Michpaul | EASY, Stage 1 | Add "tsk" sound when gripping and letting go of the gear.
6 |  | Michpaul | EASY, Stage 1 | Add "thud" sound when jumping and landing on platform.
7 |  | Michpaul | EASY, Stage 1 | Add "splash" sound when falling off the water
8 |  | Michpaul | EASY, Stage 1 | Missing audio for "Lights! Camera! Action!"
9 | 2022-03-05 | Mark | EASY, Stage 1 | (CORRECTION: too slow = before, too fast = after) On Failed Message… [NAME] spinned the gear too [fast/slow] and let go of the gear way [after/before] the release point. She did not land properly on the other side and failed the stunt! The correct answer is [ANSWER] deg/s.
10 |  | Michpaul | EASY, Stage 1 | Missing audio for "Cut!"
11 | 2022-03-05 | Mark | EASY, Stage 1 | On Success Message… [NAME] spun the gear at the correct at the correct angular velocity and let go of the gear precisely at the release point! Stunt successfully executed!
12 |  | Michpaul | EASY, Stage 1 | Avoid the player from interacting with the answer entry of the worded problem after the stunt animation
13 | 2022-02-23 | Michpaul | EASY, Stage 1 | The character should be in front of the "Landing Spot" label
14 |  | Michpaul | EASY, Stage 1 | (CRITICAL ERROR) After a wrong answer and then the reset, can no longer interact with the answer box to enter the next answer.
15 | 2022-02-23 | Michpaul | EASY, Stage 2 | Put "Landing Spot" on the target indicator
16 |  | Michpaul | EASY, Stage 2 | (CORRECTION on units: 3.2 deg/s not 3.2 s) Indicate the angular velocity of the gear as it spins
17 |  | Michpaul | EASY, Stage 2 | Make it a practice that the standard color for the correct answer is GREEN and the wrong answer is RED. Apply to both the diagram and the worded problem.
18 |  | Michpaul | EASY, Stage 2 | Green fonts with white outline should be dark green color
19 |  | Michpaul | EASY, Stage 2 | Add "tsk" sound when gripping and letting go of the gear and the pipe.
20 |  | Michpaul | EASY, Stage 2 | Add "thud" sound when jumping and landing on platform.
21 |  | Michpaul | EASY, Stage 2 | Add "splash" sound when falling off the water
22 |  | Michpaul | EASY, Stage 2 | Missing audio for "Lights! Camera! Action!"
23 | 2022-03-05 | Mark | EASY, Stage 2 | On Failed Message… [NAME] let go of the gear way too [early/late] the release point and fell down. Stunt failed! The correct answer is [ANSWER] seconds.
24 |  | Michpaul | EASY, Stage 2 | Missing audio for "Cut!"
25 |  | Michpaul | EASY, Stage 2 | On Success Message… [NAME] let go of the gear precisely at the release point and made it to the other side! Stunt successfully executed!
26 |  | Michpaul | EASY, Stage 2 | Avoid the player from interacting with the answer entry of the worded problem after the stunt animation
27 |  | Michpaul | EASY, Stage 2 | The character should be in front of the "Landing Spot" label
28 |  | Michpaul | EASY, Stage 2 | (CRITICAL ERROR) After a wrong answer and then the reset, can no longer interact with the answer box to enter the next answer.
29 |  | Michpaul | EASY, Stage 3 | Put "Landing Spot" on the target indicator
30 |  | Michpaul | EASY, Stage 3 | Indicate the angular velocity of the gear as it spins
31 |  | Michpaul | EASY, Stage 3 | Make it a practice that the standard color for the correct answer is GREEN and the wrong answer is RED. Apply to both the diagram and the worded problem.
32 |  | Michpaul | EASY, Stage 2 | Green fonts with white outline should be dark green color
33 |  | Michpaul | EASY, Stage 3 | Add "tsk" sound when gripping and letting go of the gear and the pipe.
34 |  | Michpaul | EASY, Stage 3 | Add "thud" sound when jumping and landing on platform.
35 |  | Michpaul | EASY, Stage 3 | Add "splash" sound when falling off the water
36 |  | Michpaul | EASY, Stage 3 | Missing audio for "Lights! Camera! Action!"
37 |  | Michpaul | EASY, Stage 3 | On Failed Message… [NAME] let go of the gear way too [early/late] the release point and fell down. Stunt failed! The correct answer is [ANSWER] seconds.
38 |  | Michpaul | EASY, Stage 3 | Missing audio for "Cut!"
39 |  | Michpaul | EASY, Stage 3 | On Success Message… [NAME] let go of the gear precisely at the release point and made it to the other side! Stunt successfully executed!
40 |  | Michpaul | EASY, Stage 3 | Avoid the player from interacting with the answer entry of the worded problem after the stunt animation
41 |  | Michpaul | EASY, Stage 3 | The character should be in front of the "Landing Spot" label
42 |  | Michpaul | EASY, Stage 3 | (CRITICAL ERROR) After a wrong answer and then the reset, can no longer interact with the answer box to enter the next answer.

## Forces
# | Done? | Who? | Where? | What? | Notes
1 | 2022-02-04 | Jiboy | EASY, Stage 1 | Make Zombies dark green stickmen | Used green smoke instead.
2 |  | Jiboy | EASY, Stage 1 | Indicate at the glass window its breaking Force. (based on given answer)
3 |  | Jiboy | EASY, Stage 1 | If failed, indicate at the correct breaking force of the glass window.
4 | 2022-02-23 | Jiboy | EASY, Stage 1 | Remove "exploding circle" animation on character when failed
5 | 2022-02-04 | Jiboy | EASY, Stage 1 | Make Zombies dark green stickmen
6 | 2022-02-15 | Mark | EASY, Stage 2 | On Failed Message… The breaking point of the glass is requires too [little/much] force that [NAME] ran into the glass window and [overshoots through it/unable to break it]. Stunt failed! The correct answer is [ANSWER] N.
7 | 2022-03-05 | Mark | EASY, Stage 2 | (CORRECTION: Grammar) On Success Message… The breaking point of the glass is just enougn for [NAME] to break it without overshooting. Stunt successfully executed!
8 | 2022-02-23 | Jiboy | EASY, Stage 2 | Remove "exploding circle" animation on character when failed
9 | 2022-02-23 | Jiboy | EASY, Stage 2 | Lower floor lacks translucent gray background glass window
10 |  | Jiboy | EASY, Stage 2 | Acceleration indicator should follow player
11 | 2022-03-05 | Mark | EASY, Stage 2 | On Failed Message… [NAME] ran into the glass window with too [much/little] acceleration and [overshoots through it/unable to break it]. Stunt failed! The correct answer is [ANSWER] m/s2.
12 | 2022-03-05 | Mark | EASY, Stage 2 | On Success Message… [NAME] ran with the precise acceleration just to break the glass window without overshooting. Stunt successfully executed!
13 | 2022-02-23 | Jiboy | EASY, Stage 3 | Remove "exploding circle" animation on character when failed
14 | 2022-02-23 | Jiboy | EASY, Stage 3 | Make Zombies dark green stickmen
15 | 2022-02-15 | Mark | EASY, Stage 3 | On Failed Message… [NAME] ran into the glass window carrying too [much/little] mass with [him/her] and [overshoots through it/unable to break it]. Stunt failed! The correct answer is [ANSWER] kgs.
16 | 2022-02-15 | Mark | EASY, Stage 3 | On Success Message… [NAME] ran into the glass window with the precise mass needed to break it without overshooting. Stunt successfully executed!
17 | 2022-02-23 | Jiboy | EASY, Stage 3 | No graphics on stunt completed when winning stage 3